## Agile Project Plan
ELFI PROJECT PLAN
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| ELFI | Fatma Gomaa | 2020-05-20 | 2020-06-20 |  | 60% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| PC and STM32 |  |  |  | 2022-05-20 | 2022-06-01 | 12 | Complete
| Win32 Application Implementation |  | Fatma Gomaa May A.Salam |  | 2022-09-03 | 2022-09-07 | 4 | Complete
| Win32 Application Github Documentation |  | Fatma Gomaa |  | 2022-09-03 | 2022-09-07 | 4 | Complete
| PC Application Implementation |  | Group Work |  | 2022-09-03 | 2022-09-07 | 4 | Complete
| PC Application Code Documentation |  | May A.Salam |  | 2022-09-07 | 2022-09-12 | 5 | Complete
| PC Application Github Documentation |  | Moustafa Ramdan |  | 2022-09-09 | 2022-09-13 | 4 | Complete
| TP Protocol Design and Implementation |  | Group Work |  | 2022-09-09 | 2022-09-13 | 4 | Complete
| ELF Parser Code |  | Fatma Gomaa |  | 2022-09-09 | 2022-09-13 | 4 | Complete
| Bootloader Design and Implementation |  | Group Work |  | 2022-09-09 | 2022-09-13 | 4 | Complete
| Bootloader Code Documentation |  | Mohammed A.Anis Esraa Mansour |  | 2022-09-09 | 2022-09-13 | 4 | Complete
| Bootloader Github Documentation |  | Moustafa Ramdan |  | 2022-09-09 | 2022-09-13 | 4 | Complete
| GUI Implementation |  | Donia Mohammed Moustafa Ramdan |  | 2022-09-09 | 2022-09-13 | 4 | Complete
| GUI Code Documentation |  | Moustafa Ramdan |  | 2022-05-20 | 2022-05-25 | 5 | Complete
| GUI Github Documentation |  | Donia Mohammed |  | 2022-05-20 | 2022-05-25 | 5 | Complete
| PC Application Testing |  | Fatma Gomaa May A.Salam Donia Mohammed |  | 2022-05-20 | 2022-05-25 | 5 | Complete
| STM Bootloader Testing |  | Moustafa Ramdan Mohammed A.Anis Esraa Mansour |  | 2022-05-20 | 2022-05-25 | 5 | Complete
| PC and STM32 Integration |  | Group Work |  | 2022-05-20 | 2022-05-25 | 5 | Complete
| Presentation Preparation and overall flowchart |  | Esraa Mansour Mohammed A.Anis |  | 2022-05-20 | 2022-05-25 | 5 | Complete
| Connectivity Research |  | Mohammed A.Anis Esraa Mansour |  | 2022-05-20 | 2022-05-25 | 5 | Complete
| NodeMCU and STM32 |  |  |  | 2020-06-01 | 2020-06-07 | 6 | Complete
| NodeMCU Gateway Design and implementation |  | Moustafa Ramdan Mohammed A.Anis Esraa Mansour |  | 2022-09-16 | 2022-09-17 | 1 | Complete
| NodeMCU and STM32 Communication Implementation |  | May A.Salam Fatma Gomaa |  | 2022-09-16 | 2022-09-17 | 1 | Complete
| NodeMCU and STM32 Communication Testing and Validation |  | Donia Mohammed Mohammed A.Anis |  | 2022-09-16 | 2022-09-17 | 1 | Complete
| NodeMCU Code Documentation |  | Mohammed A.Anis |  | 2022-09-16 | 2022-09-17 | 1 | Complete
| NodeMCU Github Documentation |  | Esraa Mansour |  | 2022-09-16 | 2022-09-17 | 1 | Complete
| GUI Backend CommReceive Implementation |  | Donia Mohammed Fatma Gomaa |  | 2022-09-16 | 2022-09-17 | 1 | Complete
| GUI Backend Flashing Implementation |  | Fatma Gomaa Donia Mohammed May A.Salam |  | 2022-09-16 | 2022-09-17 | 1 | Complete
| GUI Backend Code Documentation |  | Fatma Gomaa |  | 2022-09-16 | 2022-09-17 | 1 | Complete
| Reformating GUI Design |  | Mohammed A.Anis |  | 2022-09-16 | 2022-09-17 | 1 | Complete
| Integrating New GUI Design with Backend |  | Donia Mohammed Mohammed A.Anis Moustafa Ramdan |  | 2022-09-16 | 2022-09-17 | 1 | Complete
| Dependenceis Solving Script |  | Esraa Mansour Fatma Gomaa |  | 2022-09-16 | 2022-09-17 | 1 | Complete
| Inegrating GUI and NodeMCU |  | Group Work |  | 2022-09-16 | 2022-09-17 | 1 | Complete
| Flashing Scenario Testing and Validation |  | Group Work |  | 2022-09-16 | 2022-09-17 | 1 | Complete
| Portable Application Creation |  | Group Work |  | 2022-09-16 | 2022-09-17 | 1 | Complete
| Sprint 3 |  | Shari W. |  | 2022-09-25 | 2022-10-05 | 10 | Not Started
| Feature 7 |  | Alex B. |  | 2022-09-25 | 2022-09-29 | 4 | Not Started
| Feature 8 |  | Kennedy K. |  | 2022-09-24 | 2022-10-02 | 8 | Not Started
| Feature 9 |  | Jacob S. |  | 2022-10-02 | 2022-10-05 | 3 | Not Started
CLICK HERE TO CREATE IN SMARTSHEET

## Agile Project Plan - BLANK
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
Sprint 1
Feature 1
Feature 2
Feature 3
Sprint 2
Feature 4
Feature 5
Feature 6
Sprint 3
Feature 7
Feature 8
Feature 9

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.