## Agile Project Plan
ELFI PROJECT PLAN
| PROJECT NAME | PROJECT MANAGER | START DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| ELFI | Fatma Gomaa | 2020-05-20 |  | 60% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| PC and STM32 |  |  | 2020-05-20 | 2020-06-01 | 12 | Complete
| Win32 Application Implementation | Coding | Fatma Gomaa May A.Salam | 2020-05-20 | 2020-05-21 | 1 | Complete
| Win32 Application Github Documentation | Documentation | Fatma Gomaa | 2020-05-22 | 2020-05-23 | 1 | Complete
| PC Application Implementation | Coding | Group Work | 2020-05-20 | 2020-05-22 | 2 | Complete
| PC Application Code Documentation | Documentation | May A.Salam | 2020-05-24 | 2020-05-25 | 1 | Complete
| PC Application Github Documentation | Documentation | Moustafa Ramdan | 2020-05-24 | 2020-05-25 | 1 | Complete
| TP Protocol Design and Implementation | Coding | Group Work | 2020-05-22 | 2020-05-24 | 2 | Complete
| ELF Parser Code | Coding | Fatma Gomaa | 2020-05-20 | 2020-05-22 | 2 | Complete
| Bootloader Design and Implementation | Design | Group Work | 2020-05-24 | 2020-05-25 | 1 | Complete
| Bootloader Code Documentation | Documentation | Mohammed A.Anis Esraa Mansour | 2020-05-25 | 2020-05-26 | 1 | Complete
| Bootloader Github Documentation | Documentation | Moustafa Ramdan | 2020-05-26 | 2020-05-27 | 1 | Complete
| GUI Implementation | Coding | Donia Mohammed Moustafa Ramdan | 2020-05-25 | 2020-05-27 | 2 | Complete
| GUI Code Documentation | Documentation | Moustafa Ramdan | 2020-05-26 | 2020-05-27 | 1 | Complete
| GUI Github Documentation | Documentation | Donia Mohammed | 2020-05-26 | 2020-05-27 | 1 | Complete
| PC Application Testing | Testing | Fatma Gomaa May A.Salam Donia Mohammed | 2020-05-26 | 2020-05-27 | 1 | Complete
| STM Bootloader Testing | Testing | Moustafa Ramdan Mohammed A.Anis Esraa Mansour | 2020-05-26 | 2020-05-27 | 1 | Complete
| PC and STM32 Integration | Testing | Group Work | 2020-05-27 | 2020-05-28 | 1 | Complete
| Presentation Preparation and overall flowchart | Documentation | Esraa Mansour Mohammed A.Anis | 2020-05-28 | 2020-05-29 | 1 | Complete
| Connectivity Research | Research | Mohammed A.Anis Esraa Mansour | 2020-05-29 | 2020-05-30 | 1 | Complete
| NodeMCU and STM32 |  |  | 2020-06-01 | 2020-06-07 | 6 | Complete
| NodeMCU Gateway Design and implementation | Design | Moustafa Ramdan Mohammed A.Anis Esraa Mansour | 2020-06-01 | 2020-06-02 | 1 | Complete
| NodeMCU and STM32 Communication Implementation | Coding | May A.Salam Fatma Gomaa | 2020-06-02 | 2020-06-03 | 1 | Complete
| NodeMCU and STM32 Communication Testing and Validation | Testing | Donia Mohammed Mohammed A.Anis | 2020-06-02 | 2020-06-03 | 1 | Complete
| NodeMCU Code Documentation | Documentation | Mohammed A.Anis | 2020-06-02 | 2020-06-03 | 1 | Complete
| NodeMCU Github Documentation | Documentation | Esraa Mansour | 2020-06-02 | 2020-06-03 | 1 | Complete
| GUI Backend CommReceive Implementation | Coding | Donia Mohammed Fatma Gomaa | 2020-06-01 | 2020-06-02 | 1 | Complete
| GUI Backend Flashing Implementation | Coding | Fatma Gomaa Donia Mohammed May A.Salam | 2020-06-01 | 2020-06-02 | 1 | Complete
| GUI Backend Code Documentation | Documentation | Fatma Gomaa | 2020-06-02 | 2020-06-03 | 1 | Complete
| Reformating GUI Design | Design | Mohammed A.Anis | 2020-06-05 | 2020-06-06 | 1 | Complete
| Integrating New GUI Design with Backend | Coding | Donia Mohammed Mohammed A.Anis Moustafa Ramdan | 2020-06-05 | 2020-06-06 | 1 | Complete
| Dependenceis Solving Script | Coding | Esraa Mansour Fatma Gomaa | 2020-06-05 | 2020-06-06 | 1 | Complete
| Inegrating GUI and NodeMCU | Testing | Group Work | 2020-06-04 | 2020-06-05 | 1 | Complete
| Flashing Scenario Testing and Validation | Testing | Group Work | 2020-06-04 | 2020-06-05 | 1 | Complete
| Portable Application Creation | Coding | Group Work | 2020-06-05 | 2020-06-06 | 1 | Complete
| Marker Implementation and Better User Experience |  |  | 2020-06-08 | 2020-06-14 | 6 | In Progress
| Marker Implementation Design | Design | Group Work | 2020-06-08 | 2020-06-09 | 1 | Complete
| Marker Implementation Coding | Coding | Group Work | 2020-06-08 | 2020-06-09 | 1 | Complete
| Porting Application and suppress CMD | Coding | Fatma Gomaa Mohammed A.Anis Mostafa Ramdan | 2020-06-10 | 2020-06-11 | 1 | Complete
| Updating GUI with Avaiable targets and adjusting Time outs | Coding | Esraa Mansour Donia Mohammed May A.Salam | 2020-06-10 | 2020-06-12 | 2 | Complete
| Integration and Testing | Testing | Group Work | 2020-06-12 | 2020-06-13 | 1 | Complete
| Bootloader Github Documentation | Documentation | Esraa Mansour | 2020-06-13 | 2020-06-14 | 1 | Complete
| NodeMCU Github Documentation | Documentation | Fatma Gomaa | 2020-06-13 | 2020-06-14 | 1 | Complete
| Memory Sections Github Documentation | Documentation | Moustafa Ramdan | 2020-06-13 | 2020-06-14 | 1 | Complete
| Project Main Page Github Documentation | Documentation | Mohammed A.Anis | 2020-06-13 | 2020-06-14 | 1 | Complete
| ELFI Github Documentation | Documentation | May A.Salam | 2020-06-13 | 2020-06-14 | 1 | Complete
| PC Application Github Documentation | Documentation | Donia Mohammed | 2020-06-13 | 2020-06-15 | 2 | Complete